## Phase- Summary
Sl. No. | Scheme SL No | Location / Road Mark | LM | Vendor | Road Type | Length | Width | Drain | Cost In Cr (Service) | Start date | End Date
1 | 9 | IBMD Sarpa MRP- Internal Road | B K Das | GSPL | PAVER | 400 | 8 | 400 | 1.6 | 2026-12-10 | 2027-07-30
2 | 13 | PSW peripherals roads/PSW Approach roads | B K Das | BALAJI | CONCRETE | 760 | 10 | 900 | 5.4 | 2026-09-28 | 2028-01-30
3 | 22A | SMS-2 Kamag movement at BOF & Conarc/Ramp side | B K Das | JTVPL | CONCRETE | 800 | 4 | 0 | 2.1 | 2026-10-05 | 2028-01-30
4 | 22B | SMS-2 Kamag movement at BOF & Conarc/Briquetting Plant side | B K Das | GSPL | CONCRETE | 800 | 4 | 0 | 2.1 | 2026-10-07 | 2028-01-31
5 | 3 | RMPP Emergency feeding area | Lalit Swain | JTVPL | CONCRETE | 380 | 7 | 0 | 1.7 | 2026-10-05 | 2027-04-30
6 | 5 | RMPP Emergency feeding Shed | Lalit Swain | JTVPL | CONCRETE | 108 | 7 | 200 | 0.45 | 2026-12-01 | 2027-04-30
7 | 4 | RMPP Coal Shed-2 | Lalit Swain | JTVPL | CONCRETE | 100 | 7 | 0 | 0.25 | 2026-10-05 | 2027-04-30
8 | 2 | RMHS Coking Coal Yard-12 Road | Lalit Swain | CHHAYA | CONCRETE | 105 | 7 | 0 | 0.3 | 2026-10-10 | 2027-02-01
9 | 35 | BF-2 Ramp Area | S Parida | JTVPL | CONCRETE | 80 | 7 | 0 | 0.2 | 2026-10-21 | 2027-01-31
10 | 36 | BF-2 Bin Building | S Parida | BALAJI | PAVER | 170 | 6 | 80 | 0.5 | 2027-01-15 | 2027-06-30
11 | 38 | CMM SMS-1 Assembly Shop | Saroj Biswal | CHHAYA | PAVER | 200 | 6 | 0 | 0.45 | 2026-11-01 | 2027-03-05
12 | 39 | CMM SMS-1 Machine Shop | Saroj Biswal | CHHAYA | CONCRETE | 297 | 7 | 100 | 1.2 | 2026-10-25 | 2027-05-30
13 | 20 | SMS-2 Beside Torpedo rail track at Conarc | Lalit Swain | CHHAYA | CONCRETE | 100 | 4 | 0 | 0.2 | 2026-12-07 | 2027-02-24
14 | 29 | HSM Peripheral area/Gate-16 Coil Yard Road | B K Das | GSPL | CONCRETE | 100 | 8 | 0 | 0.45 | 2026-10-05 | 2027-01-10
15 | 8 | RMPP Rail siding area | B K Das | BALAJI | PAVER | 400 | 4 | 400 | 1 | 2027-04-15 | 2028-01-15
16 | 11 | Sales Yard -LD Gas holder to MRP / 14 mtr road with Culvert | B K Das | GSPL | PAVER | 110 | 14 | 110 | 0.7 | 2026-10-01 | 2027-02-27
17 | 34 | BF-1 Slag Yard | S Parida | BALAJI | CONCRETE | 155 | 7 | 100 | 0.8 | 2026-10-15 | 2027-04-30
|  | Total |  |  |  | 5065 |  | 2290 | 19.4

## Road 1 - IBMD Sarpa MRP Interna
IBMD Sarpa MRP- Internal Road/Sarpa Road & Culvert(400x8 mtr)- Paver Road- Vendor- GSPL- Manager- B K Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Six Party Clearance | Job | 1 | 2026-12-10 | 2026-12-20
2 | Excavation | Cum | 3200 | 2026-12-20 | 2027-02-28
3 | Soil Disposal | Cum | 3200 | 2026-12-20 | 2027-02-28
4 | Subgrade Preparation | Sqm | 3200 | 2027-02-25 | 2027-03-05
5 | GSB | Cum | 1120 | 2027-03-05 | 2027-04-15
6 | WMM | Cum | 480 | 2027-04-01 | 2027-05-20
7 | DLC | Cum | 480 | 2027-05-10 | 2027-05-30
8 | RCC Drain | Rmt | 400 | 2027-01-15 | 2027-05-30
9 | Paver Laying | Sqm | 3200 | 2027-05-15 | 2027-07-15
10 | Kerb wall | RMT | 1 | 2027-06-15 | 2027-07-30
Remarks-:02-11-2026

## Road 2 - PSW Approach Roads
PSW peripherals roads/PSW Approach roads (760 x 10 mtr)- Concrete Road- Vendor Name- Balaji- Manager- B K Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Vegitation clearance | No | 1 | 2026-09-28 | 2026-09-30
2 | Six Party Clearance | Job | 1 | 2026-10-01 | 2026-10-10
3 | (Heap Cutting for road diversion) | Cum | 12000 | 2026-10-12 | 2026-11-30
4 | Diversion Road Making | SQMT | 5000 | 2026-12-01 | 2026-12-30
3 | Excavation(Box Cutting) | Cum | 10000 | 2026-12-20 | 2027-02-28
4 | Soil Disposal | Cum | 22000 | 2026-10-12 | 2027-02-28
5 | GSB | Cum | 2800 | 2027-01-15 | 2027-03-30
6 | WMM | Cum | 1200 | 2027-02-20 | 2027-04-20
7 | DLC | Cum | 1200 | 2027-03-01 | 2027-05-30
8 | RCC Drain | Rmt | 900 | 2026-12-02 | 2027-06-30
9 | RCC RoAD | Cum | 2840 | 2027-05-01 | 2027-12-31
10 | Shuttering | Sqm | 6528 | 2027-05-01 | 2027-12-31
11 | Reinforcement | MT | 148 | 2027-05-01 | 2027-12-31
12 | Angle Fixing | MT | 8.2 | 2027-05-01 | 2027-12-31
13 | Bitumen Paint | Sqm | 700 | 2027-05-01 | 2027-12-31
15 | Salitex Board | Sqmt | 52 | 2027-05-01 | 2027-12-31
16 | Kerb wall | RMT | 1600 | 2027-07-20 | 2028-01-30

## Road 3 - SMS2 Ramp Side
SMS-2 Kamag movement at BOF & Conarc/Ramp side (800x4 mtr)- Concrete Road- vendor- JTVPL- Manger- B K Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date | Target/month (Cum)
1 | Dismantling | Cum | 1325 | 2026-05-10 | 30/12/2027 | 90
8 | RCC | Cum | 1120 | 15/10/2026 | 30/01/2028 | 75

## Road 4 - SMS2 Briquetting Side
SMS-2 Kamag movement at BOF & Conarc/Briquetting Plant side- Concrete Road- Vendor - GSPL- Manager - B K Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date | Target/month (Cum)
1 | Dismantling | Cum | 1325 | 2026-07-10 | 30/12/2027 | 90
2 | RCC | Cum | 1120 | 15/10/2026 | 30/01/2028 | 75

## Road 5 - RMPP Emer Feeding area
RMPP Emergency feeding area(380x7 mtr)- Concrete Road- Vendor - JTVPL-Manager- Lalit Swain
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 6400 | 2026-10-05 | 2026-12-30
2 | Soil Disposal | Cum | 6400 | 2026-10-05 | 2026-12-30
3 | Profile correction | Sqm | 2688 | 2026-12-15 | 2026-12-30
4 | GSB | Cum | 960 | 2026-10-20 | 2027-01-15
5 | WMM | Cum | 408 | 2026-10-25 | 2027-01-30
6 | DLC | Cum | 408 | 2026-11-05 | 2027-02-15
7 | PCC | Cum | 56 | 2026-11-05 | 2027-02-15
8 | RCC(reinforcemnt+shutering) | Cum | 536 | 2026-11-15 | 2027-04-20
9 | Shuttering | Sqm | 2400 | 2026-11-15 | 2027-04-15
10 | Reinforcement | MT | 40 | 2026-11-15 | 2027-04-15
11 | Kerb wall | RMT | 720 | 2026-12-15 | 2027-04-30
12 | Bitumen Paint | Sqm | 480 | 2026-11-15 | 2027-04-20
13 | Salitex board | Sqm | 24 | 2027-03-01 | 2027-04-30

## Road 6 - RMPP Emergency Feeding
RMPP Emergency feeding shed(108x7 Mtr) -Concrete Road- Vendor - JTVPL-Manager- Lalit Swain
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 850 | 2026-12-01 | 2027-01-15
2 | Soil Disposal | Cum | 850 | 2026-12-01 | 2027-01-15
1 | Profile correction | Sqm | 760 | 2027-01-17 | 2027-01-22
3 | GSB | Cum | 264 | 2027-01-22 | 2027-02-15
4 | WMM | Cum | 114 | 2027-02-16 | 2027-02-21
5 | DLC | Cum | 114 | 2027-02-24 | 2027-02-28
7 | RCC(reinforcemnt+shutering) | Cum | 160 | 2027-03-01 | 2027-04-30
6 | Shuttering | Sqm | 100 | 2027-03-01 | 2027-04-30
7 | Reinforcement | MT | 9 | 2027-03-01 | 2027-04-30
8 | Bitumen Paint | Sqm | 100 | 2027-03-01 | 2027-04-30
9 | Salitex board | Sqm | 3 | 2027-03-01 | 2027-04-30

## Road 7 - RMPP Coal Shed-2
RMPP/PCI Coal Shed-2(100x7 mtr)- Concrete Road- Vendor- JTVPL- Manager - Lalit Swain
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 1600 | 2026-10-05 | 2026-12-30
2 | Soil Disposal | Cum | 1600 | 2026-10-05 | 2026-12-30
3 | Profile correction | Sqm | 672 | 2026-12-15 | 2026-12-30
4 | GSB | Cum | 240 | 2026-10-20 | 2027-01-15
5 | WMM | Cum | 102 | 2026-10-25 | 2027-01-30
6 | DLC | Cum | 102 | 2026-11-05 | 2027-02-15
7 | PCC | Cum | 14 | 2026-11-05 | 2027-02-15
8 | RCC(reinforcemnt+shutering) | Cum | 134 | 2026-11-15 | 2027-04-20
9 | Shuttering | Sqm | 600 | 2026-11-15 | 2027-04-15
10 | Reinforcement | MT | 10 | 2026-11-15 | 2027-04-15
11 | Kerb wall | RMT | 180 | 2026-12-15 | 2027-04-30
12 | Bitumen Paint | Sqm | 120 | 2026-11-15 | 2027-04-20
13 | Salitex board | Sqm | 6 | 2027-03-01 | 2027-04-30

## Road 8 - RMHS Coking Coal Yard
RMHS Coking Coal Yard-12 Road (105x7 mtr)- Concrete Road- Vendor- Chhaya- Manager- Lalit Swain
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 900 | 2026-10-10 | 2026-11-10
2 | Soil Disposal | Cum | 900 | 2026-10-10 | 2026-11-10
3 | GSB | Cum | 275 | 2026-10-25 | 2026-11-15
4 | WMM | Cum | 125 | 2026-11-15 | 2026-11-20
5 | DLC | Cum | 125 | 2026-11-22 | 2026-11-30
6 | RCC | Cum | 165 | 2026-11-30 | 2027-01-15
6 | Shuttering | Sqm | 160 | 2026-11-30 | 2027-01-15
7 | Reinforcement | MT | 9 | 2026-11-30 | 2027-01-15
8 | Bitumen Paint | Sqm | 142 | 2026-11-30 | 2027-01-11
9 | Kerb Wall | RMT | 150 | 2027-01-15 | 2027-01-30
10 | Shalitex Board | Sqm | 3 | 2026-12-15 | 2027-02-01

## Road 9 - BF2 Ramp Area
BF-2 Ramp Area(80x7 Mtr) Concrete Road |  |  |  | 20 Mtr excavation Pending
BF-2 Ramp Area(80x7 Mtr)- Concrete Road -Vendor-JTVPL-Manager- S.Parida
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 140 | 2026-10-21 | 2026-10-26
2 | Soil Disposal | Cum | 140 | 2026-10-21 | 2026-10-26
4 | GSB | Cum | 50 | 2026-10-28 | 2026-11-03
5 | WMM | Cum | 21 | 2026-11-02 | 2026-11-06
6 | PCC | Cum | 30 | 2026-11-12 | 2026-11-17
7 | RCC | Cum | 120 | 2026-11-20 | 2027-01-14
8 | Shuttering | Sqm | 100 | 2026-11-20 | 2027-01-14
9 | Reinforcement | MT | 7 | 2026-11-20 | 2027-01-14
10 | Bitumen Paint | Sqm | 70 | 2026-11-20 | 2027-01-14
11 | Salitex board | Sqm | 3 | 2026-11-20 | 2027-01-14
12 | Kerb wall | RMT | 160 | 2027-01-15 | 2027-01-31

## Road 10 - BF2 Bin Building
BF-2 Bin Building (170x6 mtr)- Paver Road- Vendor- Balaji -Manager- S.Parida
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 1400 | 2027-01-15 | 2027-02-15
2 | Soil Disposal | Cum | 1400 | 2027-01-15 | 2027-02-15
3 | GSB | Cum | 360 | 2027-02-10 | 2027-02-28
4 | WMM | Cum | 160 | 2027-03-01 | 2027-03-30
5 | DLC | Cum | 160 | 2027-03-25 | 2027-04-10
6 | Paver Laying | Sqm | 1050 | 2027-04-02 | 2027-06-30
12 | RCC | CUM | 50 | 2027-02-01 | 2027-03-30
7 | Shuttering | Sqm | 600 | 2027-02-01 | 2027-03-30
8 | Reinforcement | MT | 3 | 2027-02-01 | 2027-03-30
9 | Angle Fixing | MT | 0.5 | 2027-02-01 | 2027-03-30
11 | Kerb wall | RMT | 350 | 2027-03-25 | 2027-06-30

## Road 11 - CMM SMS1 Assembly
CMM SMS-1 Assembly Shop( 200x6 mtr) - Paver Road- Vendor Name - Chhaya- Manager - Saroj Biswal
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 1000 | 2026-11-01 | 2026-12-10
2 | Soil Disposal | Cum | 1000 | 2026-11-01 | 2026-12-10
3 | Subgrade preparation | Sqm | 1200 | 2026-11-25 | 2026-12-12
4 | GSB | Cum | 420 | 2026-11-28 | 2026-12-20
5 | WMM | Cum | 180 | 2026-12-05 | 2026-12-25
6 | DLC | Cum | 180 | 2026-12-26 | 2026-12-31
7 | Paver Laying | Sqm | 1120 | 2026-12-25 | 2027-02-28
8 | Kerbwall | MTR | 380 | 2026-12-20 | 2027-03-05

## Road 12 - CMM SMS1 Machine Shop
CMM SMS-1 Machine Shop (297x7 Mtr)-Concrete Road-Vendor Name - Chhaya-Manager- Saroj Biswal
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Dismantling | Cum | 300 | 2026-10-25 | 2026-11-10
2 | Excavation | Cum | 2900 | 2026-11-01 | 2027-02-28
3 | Soil Disposal | Cum | 3200 | 2026-11-01 | 2027-02-28
4 | Subgrade Preparation | CSqmt | 2400 | 2027-03-01 | 2027-03-10
4 | GSB | Cum | 830 | 2026-12-15 | 2027-03-05
5 | WMM | Cum | 356 | 2027-01-01 | 2027-03-10
6 | DLC | Cum | 356 | 2027-01-20 | 2027-03-30
7 | PCC | Cum | 15 | 2027-02-01 | 2027-05-15
8 | RCC Drain | RMT | 100 | 2026-11-15 | 2027-01-15
8 | RCC | Cum | 380 | 2027-02-01 | 2027-05-15
9 | Shuttering | Sqm | 1000 | 2027-02-01 | 2027-05-15
10 | Reinforcement | MT | 30 | 2027-02-01 | 2027-05-15
11 | Angle Fixing | MT | 0.5 | 2027-02-01 | 2027-05-15
12 | Bitumen Paint | Sqm | 540 | 2027-02-01 | 2027-05-15
13 | Kerb Wall | RMT | 400 | 2027-03-15 | 2027-05-30

## Road 13 - Torpedo Rail Track
SMS-2 Beside Torpedo rail track at Conarc(100X4 mtr)- Concrete road -Vendor Name-Chhaya-Manager- Lalit swain
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 400 | 2026-12-07 | 2026-12-15
2 | Soil Disposal | Cum | 400 | 2026-12-07 | 2026-12-15
3 | Levelling &Dressing | SQM | 400 | 2026-12-16 | 2026-12-19
3 | GSB | Cum | 120 | 2026-12-21 | 2026-12-26
4 | WMM | Cum | 60 | 2026-12-28 | 2026-12-31
5 | DLC | Cum | 60 | 2027-01-01 | 2027-01-06
6 | RCC | Cum | 80 | 2027-01-11 | 2027-02-20
7 | Shuttering | Sqm | 72 | 2027-01-11 | 2027-02-20
8 | Reinforcement | MT | 5 | 2027-01-11 | 2027-02-20
9 | Bitumen Paint | Sqm | 72 | 2027-01-11 | 2027-02-20
10 | Kerb Wall | Mtr | 200 | 2027-02-01 | 2027-02-24

## Road 14 - HSM Gate16
HSM Peripheral area/Gate-16 Coil Yard Road(100x8 mtr)- Concrete Road- Vendor- GSPL- Manager- B K Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Dismentalling of Paver | CUM | 150 | 2026-10-05 | 2026-10-10
1 | Excavation | Cum | 450 | 2026-10-05 | 2026-10-12
2 | Soil Disposal | Cum | 450 | 2026-10-05 | 2026-10-12
3 | WMM | Cum | 120 | 2026-10-13 | 2026-10-26
4 | PCC | Cum | 120 | 2026-10-28 | 2026-11-10
5 | RCC | Cum | 250 | 2026-11-02 | 2026-12-30
6 | Shuttering | Sqm | 220 | 2026-11-02 | 2026-12-30
7 | Reinforcement | MT | 11 | 2026-11-02 | 2026-12-30
8 | Bitumen Paint | Sqm | 200 | 2026-11-02 | 2026-12-30
9 | Kerb Wall | RMT | 200 | 2026-12-01 | 2027-01-10

## Road 15 - RMPP Rail Siding
RMPP Rail siding area(400x4 mtr)-Paver Road-Vendor Name - Balaji-Manager - B K Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 3000 | 2027-04-15 | 2027-06-30
2 | Soil Disposal | Cum | 3000 | 2027-04-15 | 2027-06-30
3 | Levelling and Dressing | Sqmr | 2800 | 2027-05-30 | 2027-07-03
3 | GSB | Cum | 850 | 2027-06-15 | 2027-07-30
4 | WMM | Cum | 450 | 2027-07-20 | 2027-08-10
5 | DLC | Cum | 450 | 2027-08-01 | 2027-08-30
6 | Paver Laying | Sqm | 2800 | 2027-09-01 | 2027-12-30
7 | Kerbwall | RMT | 750 | 2027-11-15 | 2028-01-15

## Road 16 - Sales Yard MRP
Sales Yard -LD Gas holder to MRP/ 14 mtr road with culvert (110x14 mtr)- Paver Road- Vendor name - GSPL- Manager- B K Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 1800 | 2026-10-01 | 2026-10-30
2 | Soil Disposal | Cum | 1800 | 2026-10-01 | 2026-10-30
3 | GSB | Cum | 540 | 2026-10-20 | 2026-11-10
4 | WMM | Cum | 230 | 2026-11-05 | 2026-11-14
5 | DLC | Cum | 230 | 2026-11-16 | 2026-11-30
6 | RCC Drain | Rmt | 120 | 2026-10-05 | 2026-11-30
7 | Paver Laying | Sqm | 1540 | 2026-12-07 | 2027-02-27
8 | Kerb wall | RMT | 220 | 2026-11-30 | 2027-01-15

## Road 17 - Slag Yard
BF-1 Slag Yard(155x7 mtr)- Concrete Road- Vendor Name - Balaji -Manager- S.Parida
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 1450 | 2026-10-15 | 2026-11-25
2 | Soil Disposal | Cum | 1450 | 2026-10-15 | 2026-11-25
3 | Levelling and Dressing | Sqmr | 1085 | 2026-11-20 | 2026-11-30
3 | GSB | Cum | 350 | 2026-11-25 | 2026-12-20
4 | WMM | Cum | 165 | 2026-12-10 | 2027-01-10
5 | DLC | Cum | 165 | 2026-12-25 | 2027-01-30
6 | RCC | Cum | 250 | 2026-01-02 | 2027-04-30
6 | Shuttering | Sqm | 400 | 2026-01-02 | 2027-04-30
7 | Steel | MT | 14 | 2026-01-02 | 2027-04-30
8 | Angle | MT | 0.5 | 2026-01-02 | 2027-04-30
9 | Bitumen Paint | SQM | 185 | 2026-01-02 | 2027-04-30
10 | Kerbwall | RMT | 260 | 2026-01-02 | 2027-04-30