## Road 1 - IBMD Sarpa MRP Interna
IBMD Sarpa MRP- Internal Road/Sarpa Road & Culvert(400x8) Paver Road Vendor GSPL Manager- Bibhrat Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Six Party Clearance | Job | 1 | 10-10-206 | 2026-10-30
2 | Excavation | Cum | 3200 | 2026-11-02 | 2026-12-30
3 | Soil Disposal | Cum | 3200 | 2026-11-02 | 2026-12-30
4 | Subgrade Preparation | Sqm | 3200 | 2027-01-04 | 2027-01-12
5 | GSB | Cum | 1120 | 2027-01-13 | 2027-02-28
6 | WMM | Cum | 480 | 2027-02-25 | 2027-03-30
7 | DLC | Cum | 480 | 2027-03-22 | 2027-04-05
8 | RCC Drain | Rmt | 400 | 01-Apr-2027 | 31-Mar-2028
9 | Paver Laying | Sqm | 3200 | 2027-04-01 | 2027-06-30
10 | Kerb wall | RMT | 1 | 2027-06-15 | 2027-07-30
11 | Drain | RMT | 400 | 2027-02-01 | 2027-05-30
Remarks-:02-11-2026

## Road 2 - PSW Approach Roads
PSW peripherals roads/PSW Approach roads(400x 10) Vendor- Balaji Construction Manager- Bibhrat Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Vegitation clearance | No | 1 | 2026-09-28 | 2026-09-30
2 | Six Party Clearance | Job | 1 | 2026-10-01 | 2026-10-10
3 | Road Diversion(Heap Cutting/Temp Road ) | RMT | 1 | 2026-10-12 | 2026-10-31
3 | Excavation | Cum | 20000 | 2026-11-02 | 2027-02-28
4 | Soil Disposal | Cum | 20000 | 2026-11-02 | 2027-02-28
5 | GSB | Cum | 2800 | 2027-01-15 | 2027-03-15
6 | WMM | Cum | 1200 | 2027-02-01 | 2027-03-30
7 | DLC | Cum | 1200 | 2027-02-15 | 2027-04-15
8 | RCC Drain | Rmt | 900 | 2026-11-02 | 2027-04-30
9 | RCC RoAD | Cum | 2840 | 2027-04-15 | 2027-08-31
10 | Shuttering | Sqm | 6528 | 2027-04-15 | 2027-08-31
11 | Reinforcement | MT | 148 | 2027-04-15 | 2027-08-31
12 | Angle Fixing | MT | 8.2 | 2027-04-15 | 2027-08-31
13 | Bitumen Paint | Sqm | 700 | 2027-04-15 | 2027-08-31
14 | Drain | Mtr | 400 | 01-Apr-2027 | 31-Mar-2028
15 | Salitex Board | Sqmt | 52 | 2027-04-15 | 2027-08-31
16 | Kerb wall | RMT | 1600 | 2027-08-02 | 2027-10-30

## Road 3 - SMS2 Ramp Side
SMS-2 Kamag movement at BOF & Conarc/Ramp side(200x16) vendor- Jagdish Techno Venture Manger- Bibhrat Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Six Party Clearance | Job | 1 | 01-Apr-2027 | 31-Mar-2028
2 | Dismantling | Cum | 1325 | 01-Apr-2027 | 31-Mar-2028
3 | Excavation | Cum | 2200 | 01-Apr-2027 | 31-Mar-2028
4 | Soil Disposal | Cum | 3525 | 01-Apr-2027 | 31-Mar-2028
5 | GSB | Cum | 480 | 01-Apr-2027 | 31-Mar-2028
6 | WMM | Cum | 480 | 01-Apr-2027 | 31-Mar-2028
7 | PCC | Cum | 500 | 01-Apr-2027 | 31-Mar-2028
8 | RCC | Cum | 1120 | 01-Apr-2027 | 31-Mar-2028
9 | Shuttering | Sqm | 725 | 01-Apr-2027 | 31-Mar-2028
10 | Reinforcement | MT | 112 | 01-Apr-2027 | 31-Mar-2028
11 | Bitumen Paint | Sqm | 710 | 01-Apr-2027 | 31-Mar-2028
12 | Handover | Job | 1 | 01-Apr-2027 | 31-Mar-2028
Note - Out off 320 panel only 10 panel can be received clearance at a time . After curing period of 14 day the clearance for next panel will be avaialbel
So the total time taken will be =32x14=448 day get ideal for the Job. Job will performed for anaterh 32x10= 320 day
Total

## Road 4 - SMS2 Briquetting Side
SMS-2 Kamag movement at BOF & Conarc/Briquetting Plant side Vendor Name :- GSPL Manager :- Bibhrat Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Six Party Clearance | Job | 1 | 01-Apr-2027 | 31-Mar-2028
2 | Dismantling | Cum | 1325 | 01-Apr-2027 | 31-Mar-2028
3 | Excavation | Cum | 2200 | 01-Apr-2027 | 31-Mar-2028
4 | Soil Disposal | Cum | 3525 | 01-Apr-2027 | 31-Mar-2028
5 | GSB | Cum | 480 | 01-Apr-2027 | 31-Mar-2028
6 | WMM | Cum | 480 | 01-Apr-2027 | 31-Mar-2028
7 | PCC | Cum | 500 | 01-Apr-2027 | 31-Mar-2028
8 | RCC | Cum | 1120 | 01-Apr-2027 | 31-Mar-2028
9 | Shuttering | Sqm | 725 | 01-Apr-2027 | 31-Mar-2028
10 | Reinforcement | MT | 112 | 01-Apr-2027 | 31-Mar-2028
11 | Bitumen Paint | Sqm | 710 | 01-Apr-2027 | 31-Mar-2028
12 | Handover | Job | 1 | 01-Apr-2027 | 31-Mar-2028

## Road 5 - RMPP Emer Feeding shed
RMPP Emergency feeding shed(480x7),Kerbwall - 900 Mtr, Concrete Road vendor name - Jagdish Techno Venture Manager:- Lalit Swain
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 8000 | 2026-10-05 | 2026-12-30
2 | Soil Disposal | Cum | 8000 | 2026-10-05 | 2026-12-30
3 | Profile correction | Sqm | 3360 | 2026-12-15 | 2026-12-30
4 | GSB | Cum | 1200 | 2026-10-20 | 2027-01-15
5 | WMM | Cum | 510 | 2026-10-25 | 2026-01-30
6 | DLC | Cum | 510 | 2026-11-05 | 2027-02-15
7 | PCC | Cum | 70 | 2026-11-05 | 2027-02-15
8 | RCC(reinforcemnt+shutering) | Cum | 670 | 2026-11-15 | 2027-04-20
9 | Shuttering | Sqm | 3000 | 2026-11-15 | 2027-04-15
10 | Reinforcement | MT | 50 | 2026-11-15 | 2027-04-15
11 | Kerb wall | RMT | 900 | 2026-12-15 | 2027-04-30
12 | Bitumen Paint | Sqm | 600 | 2026-11-15 | 2027-04-20
13 | Salitex board | Sqm | 30 | 2027-03-01 | 2027-04-30

## Road 6 - RMPP Emergency Feeding
RMPP Emergency feeding Area(108x7 Mtr) Concrete road vendor name - Jagdish Techno Venture Manager:- Lalit Swain
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 850 | 2026-12-01 | 2027-01-15
2 | Soil Disposal | Cum | 850 | 2026-12-01 | 2027-01-15
1 | Profile correction | Sqm | 760 | 2027-01-17 | 2027-01-22
3 | GSB | Cum | 264 | 2027-01-22 | 2027-02-15
4 | WMM | Cum | 114 | 2027-02-16 | 2027-02-21
5 | DLC | Cum | 114 | 2027-02-24 | 2027-02-28
7 | RCC(reinforcemnt+shutering) | Cum | 160 | 2027-03-01 | 2027-04-30
6 | Shuttering | Sqm | 100 | 2027-03-01 | 2027-04-30
7 | Reinforcement | MT | 9 | 2027-03-01 | 2027-04-30
8 | Bitumen Paint | Sqm | 100 | 2027-03-01 | 2027-04-30
9 | Salitex board | Sqm | 3 | 2027-03-01 | 2027-04-30

## Road 7 - RMPP Coal Shed-2
RMPP/PCI Coal Shed-2(250x7) Vendor- GSPL Concrete Road-Kerb wall 450 Mtr Manager :- Lalit Swain
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 2000 | 2027-02-15 | 2027-03-31
2 | Soil Disposal | Cum | 2000 | 2027-02-15 | 2027-03-31
3 | Subgrade preparation | Sqmt | 1800 | 2027-04-01 | 2027-04-10
3 | GSB | Cum | 650 | 2027-04-05 | 2027-04-25
4 | WMM | Cum | 275 | 2027-04-20 | 2027-05-10
5 | DLC | Cum | 275 | 2027-05-10 | 2027-05-30
6 | RCC | Cum | 350 | 2027-05-20 | 2027-08-20
7 | Shuttering | Sqm | 380 | 2027-05-20 | 2027-08-20
8 | Reinforcement | MT | 21 | 2027-05-20 | 2027-08-20
9 | Bitumen Paint | Sqm | 340 | 2027-05-20 | 2027-08-20
10 | Salitex Board | SQm | 12 | 2027-05-20 | 2027-08-20
11 | Kerb wall | RMT | 450 | 2027-08-01 | 2027-09-15

## Road 8 - RMHS Coking Coal Yard
Vendor Name- Chhaya Trader |  |  | Line Manger-Lalit Swain
RMHS Coking Coal Yard-12 Road (105x7 ) Concrete Road
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 900 | 2026-10-10 | 2026-11-10
2 | Soil Disposal | Cum | 900 | 2026-10-10 | 2026-11-10
3 | GSB | Cum | 275 | 2026-10-25 | 2026-11-15
4 | WMM | Cum | 125 | 2026-11-15 | 2026-11-20
5 | DLC | Cum | 125 | 2026-11-22 | 2026-11-30
6 | RCC | Cum | 165 | 2026-11-30 | 2027-01-15
6 | Shuttering | Sqm | 160 | 2026-11-30 | 2027-01-15
7 | Reinforcement | MT | 9 | 2026-11-30 | 2027-01-15
8 | Bitumen Paint | Sqm | 142 | 2026-11-30 | 2027-01-11
9 | Kerb Wall | RMT | 150 | 2027-01-15 | 2027-01-30
10 | Shalitex Board | Sqm | 3 | 2026-12-15 | 2027-02-01

## Road 9 - BF2 Ramp Area
BF-2 Ramp Area(80x7 Mtr) Concrete Road |  |  |  | 20 Mtr excavation Pending
BF-2 Ramp Area(80x7 Mtr) Concrete Road Manager- S.Parida Vendor-Jagdish techno venture
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 140 | 2026-10-21 | 2026-10-26
2 | Soil Disposal | Cum | 140 | 2026-10-21 | 2026-10-26
4 | GSB | Cum | 50 | 2026-10-28 | 2026-10-26
5 | WMM | Cum | 21 | 2026-11-02 | 2026-11-06
6 | PCC | Cum | 30 | 2026-11-12 | 2026-11-17
7 | RCC | Cum | 120 | 2026-11-20 | 2027-01-14
8 | Shuttering | Sqm | 100 | 2026-11-20 | 2027-01-14
9 | Reinforcement | MT | 7 | 2026-11-20 | 2027-01-14
10 | Bitumen Paint | Sqm | 70 | 2026-11-20 | 2027-01-14
11 | Salitex board | Sqm | 3 | 2026-11-20 | 2027-01-14
12 | Kerb wall | RMT | 160 | 2027-01-15 | 2027-01-31

## Road 10 - BF2 Bin Building
BF-2 Bin Building-Paver Road(170x6) Drain -80 Mtr,Culvert-15 RMT vendor name:- Balaji Construction Manager:- S.Parida
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 1400 | 2026-10-15 | 2026-12-30
2 | Soil Disposal | Cum | 1400 | 2026-10-15 | 2026-12-30
3 | GSB | Cum | 360 | 2026-12-15 | 2027-01-30
4 | WMM | Cum | 160 | 2027-02-01 | 2026-02-28
5 | DLC | Cum | 160 | 2027-03-01 | 2027-03-10
6 | Paver Laying | Sqm | 1050 | 2027-03-12 | 2026-04-30
12 | RCC | CUM | 50 | 2026-11-01 | 2027-01-15
7 | Shuttering | Sqm | 600 | 2026-11-01 | 2027-01-15
8 | Reinforcement | MT | 3 | 2026-11-01 | 2027-01-15
9 | Angle Fixing | MT | 0.5 | 2026-11-01 | 2027-01-15
11 | Kerb wall | RMT | 350 | 2026-11-15 | 2027-02-15

## Road 11 - CMM SMS1 Assembly
CMM SMS-1 Assembly Shop( 200x6 mtr) vendor Name :- Chhaya Trader manager :- Saroj Biswal
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 1000 | 2026-11-01 | 2026-12-10
2 | Soil Disposal | Cum | 1000 | 2026-11-01 | 2026-12-10
3 | Subgrade preparation | Sqm | 1200 | 2026-11-25 | 2026-12-12
4 | GSB | Cum | 420 | 2026-11-28 | 2026-12-20
5 | WMM | Cum | 180 | 2026-12-05 | 2026-12-25
6 | DLC | Cum | 180 | 2026-12-26 | 2026-12-31
7 | Paver Laying | Sqm | 1120 | 2026-12-25 | 2027-02-28
8 | Kerbwall | MTR | 380 | 2026-12-20 | 2027-03-05

## Road 12 - CMM SMS1 Machine Shop
CMM SMS-1 Machine Shop(297x8 Mtr) Concrete Road Drain - 100 MTr Culvert-3 nos vendor Name :- Chhaya Trader manager :- Saroj Biswal
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Dismantling | Cum | 300 | 2026-10-25 | 2026-11-10
2 | Excavation | Cum | 2900 | 2026-11-01 | 2027-02-28
3 | Soil Disposal | Cum | 3200 | 2026-11-01 | 2027-02-28
4 | Subgrade Preparation | CSqmt | 2400 | 2027-03-01 | 2027-03-10
4 | GSB | Cum | 830 | 2026-12-15 | 2027-03-05
5 | WMM | Cum | 356 | 2027-01-01 | 2027-03-10
6 | DLC | Cum | 356 | 2027-01-20 | 2027-03-30
7 | PCC | Cum | 15 | 2027-02-01 | 2027-05-15
8 | RCC Drain | RMT | 100 | 2026-11-15 | 2027-01-15
8 | RCC | Cum | 380 | 2027-02-01 | 2027-05-15
9 | Shuttering | Sqm | 1000 | 2027-02-01 | 2027-05-15
10 | Reinforcement | MT | 30 | 2027-02-01 | 2027-05-15
11 | Angle Fixing | MT | 0.5 | 2027-02-01 | 2027-05-15
12 | Bitumen Paint | Sqm | 540 | 2027-02-01 | 2027-05-15
13 | Kerb Wall | RMT | 400 | 2027-03-15 | 2027-05-30

## Road 13 - Torpedo Rail Track
SMS-2 Beside Torpedo rail track at Conarc(100X4) Concrete road manager- Lalit swain vendor :- Chhaya Trader
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 400 | 2026-12-07 | 2026-12-15
2 | Soil Disposal | Cum | 400 | 2026-12-07 | 2026-12-15
3 | Levelling &Dressing | SQM | 400 | 2026-12-16 | 2026-12-19
3 | GSB | Cum | 120 | 2026-12-21 | 2026-12-26
4 | WMM | Cum | 60 | 2026-12-28 | 2026-12-31
5 | DLC | Cum | 60 | 2027-01-01 | 2027-01-06
6 | RCC | Cum | 80 | 2027-01-11 | 2027-02-20
7 | Shuttering | Sqm | 72 | 2027-01-11 | 2027-02-20
8 | Reinforcement | MT | 5 | 2027-01-11 | 2027-02-20
9 | Bitumen Paint | Sqm | 72 | 2027-01-11 | 2027-02-20
10 | Kerb Wall | Mtr | 200 | 2027-02-01 | 2026-02-24

## Road 14 - HSM Gate16
HSM Peripheral area/Gate-16 Coil Yard Road(100x8) Concrete Road Vendor:- GSPL Manager :- Bibhrat Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Dismentalling of Paver | CUM | 150 | 2026-10-05 | 2026-10-10
1 | Excavation | Cum | 450 | 2026-10-05 | 2026-10-12
2 | Soil Disposal | Cum | 450 | 2026-10-05 | 2026-10-12
3 | WMM | Cum | 120 | 2026-10-13 | 2026-10-26
4 | PCC | Cum | 120 | 2026-10-28 | 2026-11-10
5 | RCC | Cum | 250 | 2026-11-02 | 2026-12-30
6 | Shuttering | Sqm | 220 | 2026-11-02 | 2026-12-30
7 | Reinforcement | MT | 11 | 2026-11-02 | 2026-12-30
8 | Bitumen Paint | Sqm | 200 | 2026-11-02 | 2026-12-30
9 | Kerb Wall | RMT | 200 | 2026-12-01 | 2027-01-10

## Road 15 - RMPP Rail Siding
RMPP Rail siding area(400x7) Paver Road-Balaji Construction-Manager-Bibhrat Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 3000 | 2027-04-15 | 2027-06-30
2 | Soil Disposal | Cum | 3000 | 2027-04-15 | 2027-06-30
3 | Levelling and Dressing | Sqmr | 2800 | 2027-05-30 | 2027-07-03
3 | GSB | Cum | 850 | 2027-06-15 | 2027-07-30
4 | WMM | Cum | 450 | 2027-07-20 | 2027-08-10
5 | DLC | Cum | 450 | 2027-08-01 | 2027-08-30
6 | Paver Laying | Sqm | 2800 | 2027-09-01 | 2027-12-30
7 | Kerbwall | RMT | 750 | 2027-11-15 | 2028-01-15

## Road 16 - Sales Yard MRP
Sales Yard -LD Gas holder to MRP(110x14) Paver Vendro - GSPL- Manager- Bibhrat Das
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 1800 | 2026-10-01 | 2026-10-30
2 | Soil Disposal | Cum | 1800 | 2026-10-01 | 2026-10-30
3 | GSB | Cum | 540 | 2026-10-20 | 2026-11-10
4 | WMM | Cum | 230 | 2026-11-05 | 2026-11-14
5 | DLC | Cum | 230 | 2026-11-16 | 2026-11-30
6 | RCC Drain | Rmt | 120 | 2026-10-05 | 2026-11-30
7 | Paver Laying | Sqm | 1540 | 2026-12-07 | 2027-02-27
8 | Kerb wall | RMT | 220 | 2026-11-30 | 2027-01-15

## Road 17 - Slag Yard
Slag Yard(155x7.0) vendor- Balaji Construction Manager- Subhashih Parida-Concrete Road
Sl No | Description of Job | Unit | Quantity | Start Date | End Date
1 | Excavation | Cum | 1450 | 2026-01-04 | 2027-02-20
2 | Soil Disposal | Cum | 1450 | 2026-01-04 | 2027-02-20
3 | Levelling and Dressing | Sqmr | 1085 | 2027-02-22 | 2027-03-05
3 | GSB | Cum | 350 | 2027-03-08 | 2027-04-10
4 | WMM | Cum | 165 | 2027-04-10 | 2027-04-30
5 | DLC | Cum | 165 | 2027-05-03 | 2027-05-22
6 | RCC | Cum | 250 | 2027-06-01 | 2027-08-30
6 | Shuttering | Sqm | 400 | 2027-06-01 | 2027-08-30
7 | Steel | MT | 14 | 2027-06-01 | 2027-08-30
8 | Angle | MT | 0.5 | 2027-06-01 | 2027-08-30
9 | Bitumen Paint | SQM | 185 | 2027-06-01 | 2027-08-30
10 | Kerbwall | RMT | 260 | 2027-08-25 | 2027-09-30